## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | M.A.V.R.I.C.
Team name | Mechanical
Team Leader Name | Kyle Helvie
Week Number | 7
Attendance Records
Number of Students Present | 8
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status for the team:
Suspension has run into a snag regarding shocks. Shocks have ended up too heavy, and as a result the suspension cuts too heavily into our mass budget. As a result, we're revising suspension geometry to try and have access to a wider range of shocks and are also in the inital design stages of our own, lighter, shocks. CAD as a result should be a little bit tight timing wise, but if suspension geometry hammered out before shock an assembly can be made that will just require shocks to be inserted once completed.
Task Report
Milestone/Task | Due Date | Progress | Status
Milestone 1: Design | 2017-10-17 | 45.5% | On Track
Chassis CAD | 2017-10-07 | 100% | On Track
Mounting Points | 2017-10-07 | 70% | On Track
Suspension CAD | 2017-10-17 | 50% | On Track
Electrical Box CAD | 2017-10-07 | 75% | On Track
Robotic Arm CAD | 2017-10-07 | 30% | On Track
Base Rotation | 2017-10-07 | 75% | On Track
Potentiometer Mount | 2017-10-07 | 5% | On Track
End Effector/Science Attachment | 2017-10-07 | 50% | On Track
Parts List and Budgeted | 2017-10-17 | 0% | On Track
Integrated Assembly | 2017-10-17 | 0% | On Track
Milestone 2: Manufacturing | 2017-11-07 | 12.31% | On Track
Chassis Manufacturing | 2017-10-17 | 50% | On Track
Quality Manufacturing Sponsorship | 2017-09-25 | 100% | On Track
Suspension Test Manufacture/Assembly | 2017-11-03 | 0% | On Track
Order/Test One Shock | 2017-10-31 | 0% | On Track
Waterjet/Manfacture Components | 2017-10-31 | 0% | On Track
Assemble and Test Suspension | 2017-11-03 | 0% | On Track
Electrical Box Wooden Testbed | 2017-10-10 | 10% | On Track
Electrical Box Manufacture | 2017-10-28 | 0% | On Track
Mounting Hardware Manufacture | 2017-10-28 | 0% | On Track
Robotic Arm Manufacture/Assembly | 2017-11-03 | 0% | On Track
Misc. Manufacture | 2017-10-31 | 0% | On Track
Design Robotic Arm Testing Rig | 2017-10-14 | 0% | On Track
Manufacture Arm Testing Rig (TIG Training) |  | 0% | On Track
Milestone 3: Assembly | 2017-12-02 | 0% | On Track
Suspension Manufacture | 2017-11-14 | 0% | On Track
Suspension Assembly | 2017-11-24 | 0% | On Track
Electrical Box Assembly | 2017-11-14 | 0% | On Track
Chassis Assembly | 2017-11-14 | 0% | On Track
Robotic Arm Off-Rover Testing | 2017-12-02 | 0% | On Track
Mounting Assembly (TIG Welding) | 2017-11-19 | 0% | On Track
Milestone 4: Testing | 2017-12-14 | 0% | On Track
LOS Driving Tests | 2017-12-14 | 0% | On Track
Robotic Arm On-Rover Testing | 2017-12-14 | 0% | On Track
NLOS Driving Tests | 2017-12-14 | 0% | On Track
Difficult Terrain Navigation Tests | 2017-12-14 | 0% | On Track
Robotic Arm Fine Manipulation Tests | 2017-12-14 | 0% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1: Design | Mechanical Team | 2017-08-21 | 2017-10-17 | 57 | 45.5%
1.1 | Chassis CAD | Derick | 2017-09-05 | 2017-10-07 | 32 | 100% | bar: WEEK 3 M to WEEK 7 F
1.1.1 | Mounting Points | Rebecka/Matthew | 2017-09-05 | 2017-10-07 | 32 | 70% | bar: WEEK 3 M to WEEK 7 F
1.2 | Suspension CAD | Kai Davis/Jefferson O'Brien | 2017-09-05 | 2017-10-17 | 42 | 50% | bar: WEEK 3 M to WEEK 7 F
1.3 | Electrical Box CAD | Riley | 2017-09-12 | 2017-10-07 | 25 | 75% | bar: WEEK 4 R to WEEK 7 F
1.4 | Robotic Arm CAD | Kyle | 2017-09-12 | 2017-10-07 | 25 | 30% | bar: WEEK 4 R to WEEK 7 F
1.4.1 | Base Rotation | Hubert/Chris | 2017-09-19 | 2017-10-07 | 18 | 75% | bar: WEEK 5 T to WEEK 7 F
1.4.2 | Potentiometer Mount | Rebecka/Matthew | 2017-09-30 | 2017-10-07 | 7 | 5% | bar: WEEK 6 F to WEEK 7 F
1.4.3 | End Effector/Science Attachment |  | 2017-10-03 | 2017-10-07 | 4 | 50% | bar: WEEK 6 F; WEEK 7 T to WEEK 8 T
1.5 | Parts List and Budgeted | Kyle | 2017-10-07 | 2017-10-17 | 10 | 0% | bar: WEEK 6 F; WEEK 7 F to WEEK 8 T
1.6 | Integrated Assembly | Kyle | 2017-10-07 | 2017-10-17 | 10 | 0% | bar: WEEK 6 F; WEEK 7 F to WEEK 8 T
2 | Milestone 2: Manufacturing | Mechanical Team | 2017-10-03 | 2017-11-07 | 35 | 12.31%
2.1 | Chassis Manufacturing | Quality Manufacturing | 2017-09-25 | 2017-10-17 | 22 | 50% | bar: WEEK 6 M to WEEK 9 T
2..1.1 | Quality Manufacturing Sponsorship | Gage/Derick | 2017-09-25 | 2017-09-25 | 0 | 100% | bar: WEEK 6 M; WEEK 8 M to WEEK 8 F
2.2 | Suspension Test Manufacture/Assembly | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-11-03 | 17 | 0% | bar: WEEK 8 M to WEEK 11 F
2.2.1 | Order/Test One Shock | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-10-31 | 14 | 0% | bar: WEEK 8 M to WEEK 11 F
2.2.2 | Waterjet/Manfacture Components | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-10-31 | 14 | 0% | bar: WEEK 8 M to WEEK 11 F
2.2.3 | Assemble and Test Suspension | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-11-03 | 17 | 0% | bar: WEEK 8 M to WEEK 11 F
2.3 | Electrical Box Wooden Testbed | Riley/Kyle | 2017-10-03 | 2017-10-10 | 7 | 10% | bar: WEEK 7 T to WEEK 11 F
2.4 | Electrical Box Manufacture | Riley/Kyle | 2017-10-13 | 2017-10-28 | 15 | 0% | bar: WEEK 8 M to WEEK 8 F
2.5 | Mounting Hardware Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-28 | 15 | 0% | bar: WEEK 8 M to WEEK 8 F
2.6 | Robotic Arm Manufacture/Assembly | Hubert/Chris/Kyle | 2017-10-13 | 2017-11-03 | 21 | 0% | bar: WEEK 8 M to WEEK 11 F
2.7 | Misc. Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | 18 | 0% | bar: WEEK 8 M to WEEK 11 F
2.8 | Design Robotic Arm Testing Rig | Rebecka | 2017-10-07 | 2017-10-14 | 7 | 0% | bar: WEEK 7 F to WEEK 8 F
2.9 | Manufacture Arm Testing Rig (TIG Training) | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | 18 | 0% | bar: WEEK 8 M to WEEK 11 F
| Milestone 3: Assembly | Mechanical Team | 2017-10-28 | 2017-12-02 | 35 | 0%
3.1 | Suspension Manufacture | Mechanical Team | 2017-11-07 | 2017-11-14 | 7 | 0% | bar: WEEK 8 M to WEEK 8 F
3.2 | Suspension Assembly | Mechanical Team | 2017-11-14 | 2017-11-24 | 10 | 0% | bar: WEEK 8 M to WEEK 8 F
3.3 | Electrical Box Assembly | Riley/Kyle | 2017-10-28 | 2017-11-14 | 17 | 0% | bar: WEEK 8 M to WEEK 8 F
3.4 | Chassis Assembly | Derick/Rebecka/Matthew | 2017-10-28 | 2017-11-14 | 17 | 0% | bar: WEEK 8 M to WEEK 8 F
3.5 | Robotic Arm Off-Rover Testing | Kyle/Hubert/Chris | 2017-11-07 | 2017-12-02 | 25 | 0% | bar: WEEK 8 M to WEEK 8 F
3.6 | Mounting Assembly (TIG Welding) | Hubert/Chris/Other(?) | 2017-10-28 | 2017-11-19 | 22 | 0% | bar: WEEK 8 M to WEEK 8 F
| Milestone 4: Testing | Mechanical Team | 2017-12-02 | 2017-12-14 | 12 | 0%
3.1 | LOS Driving Tests |  | 2017-12-02 | 2017-12-14 | 12 | 0% | bar: WEEK 8 M to WEEK 8 F
3.2 | Robotic Arm On-Rover Testing |  | 2017-12-02 | 2017-12-14 | 12 | 0% | bar: WEEK 8 M to WEEK 8 F
3.3 | NLOS Driving Tests |  | 2017-12-02 | 2017-12-14 | 12 | 0% | bar: WEEK 8 M to WEEK 8 F
3.4 | Difficult Terrain Navigation Tests |  | 2017-12-02 | 2017-12-14 | 12 | 0% | bar: WEEK 8 M to WEEK 8 F
3.4 | Robotic Arm Fine Manipulation Tests |  | 2017-12-02 | 2017-12-14 | 12 | 0% | bar: WEEK 8 M to WEEK 8 F
Formulas:
START DATE = [DUE DATE, row above]

## Attendance Records
NetID | First Name | Last Name | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Total
| Stephen | Davis | P | P | P | P | P | [9 empty] | 5
| Matthew | Matjeka | P | P | P | P | P | [9 empty] | 0
| Rebecka | Ogle | P | P | P | P | P | [9 empty] | 0
| Hubert | Ooi | P | P | P | P | P | [9 empty] | 0
| Riley | Roche | P | P | P | P | P | [9 empty] | 0
| Derick | Whited | P | P | P | P | P | [9 empty] | 0
| Christopher | Wong | P | P | P | P | P | [9 empty] | 0
0
Key: | P | Present
| NP | Not Present

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track