## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Misc/Strategy Team
Team Leader Name | Gabe Gatmaitan
Week Number | 13
Attendance Records
Number of Students Present | 2
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
This week was a productive week in MAVRIC, as we finished our CDR. With large redesigns happening with the other teams, our advising played a big role in helping each time with their needed changes. Rover simulator is continued being worked on, game elements being mostly done, with the only issue being us waiting for the Mecahical team's design so we could add the correct rover and dimentions to the game. MAVRIC Cockpit is also close to finished, as we are just still waiting on the amazon order to come in
Task Report
Milestone/Task | Due Date | Progress | Status
MAVRIC Team Technical Advising | 2017-12-01 | 60% | On Track
Advise E-Team | 2017-12-01 | 60% | On Track
Advise Science Team | 2017-12-01 | 60% | On Track
Advise Mechanical Team | 2017-12-01 | 60% | On Track
Rover Simulator | 2017-11-18 | 80% | On Track
Basic controls | 2017-10-06 | 100% | On Track
Camera feedback | 2017-10-14 | 100% | On Track
Rover rigging | 2017-10-28 | 70% | On Track
MAVRIC Cockpit | 2017-10-28 | 87.5% | On Track
Decide on Cockpit style | 2017-10-14 | 100% | On Track
Build control system/hardware | 2017-11-20 | 75% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | MAVRIC Team Technical Advising |  |  | 2017-12-01 |  | 60%
1.1 | Advise E-Team | Gabe/Isaiah | 2017-09-12 | 2017-12-01 |  | 60% | bar: WEEK 3 M to WEEK 3 F
1.2 | Advise Science Team | Gabe/Isaiah | 2017-09-12 | 2017-12-01 |  | 60% | bar: WEEK 4 M to WEEK 6 F
1.3 | Advise Mechanical Team | Gabe/Isaiah | 2017-09-12 | 2017-12-01 |  | 60% | bar: WEEK 7 M to WEEK 9 F
0%
0%
0%
0%
2 | Rover Simulator |  |  | 2017-11-18 |  | 80%
2.1 | Basic controls | Isaiah | 2017-09-12 | 2017-10-06 |  | 100%
2.1.1 | Camera feedback | Isaiah | 2017-09-12 | 2017-10-14 |  | 100%
2.2 | Rover rigging | Isaiah | 2017-09-12 | 2017-10-28 |  | 70%
2.3 | Game elements (Objectives/Tasks) | Isaiah | 2017-09-12 | 2017-11-18 |  | 50%
| MAVRIC Cockpit |  |  | 2017-10-28 |  | 87.5%
4.1 | Decide on Cockpit style | Isaiah | 2017-09-12 | 2017-10-14 |  | 100%
4.2 | Build control system/hardware | Gabe | 2017-09-12 | 2017-11-20 |  | 75%
0%
0%
0%
0%

## Attendance Records
NetID | First Name | Last Name | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Total
isaiahe | Isaiah | Exley-Schuman | P | P | P | P | P | P | P | P | P | P | P |  |  |  | 11
gabegat | Gabe | Gatmaitan | P | P | P | P | P | P | P | P | P | P | P |  |  |  | 11
0
0
0
0
0
0
Key: | P | Present
| NP | Not Present

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track