## Sheet1
| Task | Team Member | Start | End | Duration | Percent Complete
Electrical
1 | Setting up
1.1 | Assign Roles | James Talbert | 2017-09-14 | 2017-09-20
1.2 | Getting E box from Mechanical team |  | 2017-08-21 | 2017-09-27
2 | Drive system |  |  | 2017-11-12
2.1 | Do reasearch | Split among team | 2017-09-14 | 2017-09-27
2.2 | Power systems | Jake Raymer | 2017-09-21 | 2017-10-04
2.3 | Control systems | Jefferson O'Brien | 2107-09-21 | 2017-10-04
2.4 | Firmware | Alex Vande Loo | 2017-09-21 | 2017-10-11
2.5 | Circuits CAD | Morgan Foley | 2017-09-21 | 2017-10-11
3 | Refinement |  |  | 2017-11-27
3.1 | Firmware | Alex Vande Loo
3.2 | Circuits | Morgan Foley
3.3 | Controls | Jefferson O'Brien
4 | Arm Control |  |  | 2017-12-03
4.1 | Hardware Drivers | Morgan Foley
4.2 | Firmware Drivers | Alex Vande Loo
4.3 | Controls | Jefferson O'Brien
4.4 | Power systems | Jake Raymer
Strategy
1 | Technical Advising
1.1 | Advise E-Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
1.2 | Advise Science Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
1.3 | Advise Mechanical Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
2 | Rover Simulator
2.1 | Basic Controls | Isaiah | 2017-09-12 | 2017-12-01
2.2 | Camera feedback | Isaiah | 2017-09-12 | 2017-12-01
2.3 | Rover Rigging | Isaiah | 2017-09-12 | 2017-12-01
2.4 | Game elements | Isaiah | 2017-09-12 | 2017-12-01
3 | Website upkeep
3.1 | Transfer to new site | Gabe | 2017-09-12 | 2017-10-30
3.2 | Update photos and info of team members | Gabe | 2017-09-12 | 2017-10-30
3.3 | General updates and upkeep | Gabe | 2017-09-12 | 2017-10-30
4 | Mavric Cockpit
4.1 | Decide on Cockpit Style | Isaiah | 2017-09-12 | 2017-10-30
4.2 | Build Control system / Hardware | Gabe | 2017-09-12 | 2017-12-01
Science
1 | Milestone 1 - Research
1.1 | Investigate different soil gathering methods |  | 2017-09-04 | 2017-09-15
1.2 | Investigate different soil analysis tests |  | 2017-09-04 | 2017-09-15
1.3 | Tabulate all competition requirements into Pugh Matrix |  | 2017-09-06 | 2017-09-11
1.4 | Agree on on-board tests |  |  | 2017-09-20
1.5 | Agree on mechanical design |  |  | 2017-09-20
1.6 | Obtain soil from Utah |  | 2017-09-20 | 2017-09-26
2 | Milestone 2 - Design
2.1 | complete CAD of collection subsystem |  | 2017-09-13 | 2017-09-25
2.2 | parts list |  | 2017-09-20 | 2017-09-22
2.3 | order sensors, rods, motor |  | 2017-09-18 | 2017-09-27
2.4 | 3D print as needed |  |  | 2017-10-06
2.5 | order spectroscope |  | 2017-09-22 | 2017-09-26
2.6 | complete CAD of attachment subsystem |  | 2017-09-25 | 2017-09-27
2.6.1 | parts list |  |  | 2017-09-27
2.6.2 | order parts |  |  | 2017-09-27
2.7 | complete CAD of spectroscope subsystem |  |  | 2017-09-29
2.7.1 | parts list |  |  | 2017-09-29
2.7.2 | order parts |  |  | 2017-09-29
3 | Milestone 3 - Testing
3.1 | receive spectroscope |  |  | 2017-09-26
3.1.1 | find out how much dilution is needed
3.1.2 | compile emission spectrum library/description for different soil types
3.1.3 | multiple trials
3.2 | receive motor
3.2.1 | punch test for motor
3.3 | receive temp and moisture sensor
3.3.2 | test and calibrate
3.4 | assemble and test spectroscope system
4 | Milestone 4 - Assembly
4.1 | assemble collection system, spectroscope system, arm attachment
4.2 | integrate with arm
4.2.1 | electronics, wiring, coding
4.3 | plan for base station procedures in Spring
1 | Milestone 1: Design | Mechanical Team | 2017-08-21 | 2017-10-13 | 53 | 75%
1.1 | Chassis CAD | Derick | 2017-09-05 | 2017-10-07 | 32 | 25%
1.1.1 | Mounting Points | Rebecka/Matthew | 2017-09-05 | 2017-10-07 | 32 | 75%
1.2 | Suspension CAD | Kai Davis/Jefferson O'Brien | 2017-09-05 | 2017-10-07 | 32 | 50%
1.3 | Electrical Box CAD | Riley | 2017-09-12 | 2017-10-07 | 25 | 25%
1.4 | Robotic Arm CAD | Kyle | 2017-09-12 | 2017-10-07 | 25 | 75%
1.4.1 | Base Rotation | Hubert/Chris | 2017-09-19 | 2017-10-07 | 18 | 0%
1.4.2 | Potentiometer Mount | Rebecka/Matthew | 2017-09-30 | 2017-10-07 | 7 | 0%
1.4.3 | End Effector/Science Attachment |  | 2017-10-03 | 2017-10-07 | 4 | 0%
1.5 | Parts List and Budgeted | Kyle | 2017-10-07 | 2017-10-10 | 3 | 0%
1.6 | Integrated Assembly | Kyle | 2017-10-07 | 2017-10-10 | 3 | 7.692%
2 | Milestone 2: Manufacturing | Mechanical Team | 2017-10-03 | 2017-11-07 | 35 | 0%
2.1 | Chassis Manufacturing | Quality Manufacturing | 2017-09-25 | 2017-10-17 | 22 | 100%
2..1.1 | Quality Manufacturing Sponsorship | Gage/Derick | 2017-09-25 | 2017-09-25 | 0
2.2 | Suspension Test Manufacture/Assembly | Kai Davis/Jefferson O'Brien | 2017-10-13 | 2017-11-03 | 21
2.2.1 | Order/Test One Shock | Kai Davis/Jefferson O'Brien | 2017-10-13 | 2017-10-31 | 18
2.2.2 | Waterjet/Manfacture Components | Kai Davis/Jefferson O'Brien | 2017-10-13 | 2017-10-31 | 18
2.2.3 | Assemble and Test Suspension | Kai Davis/Jefferson O'Brien | 2017-10-13 | 2017-11-03 | 21
2.3 | Electrical Box Wooden Testbed | Riley/Kyle | 2017-10-03 | 2017-10-10 | 7
2.4 | Electrical Box Manufacture | Riley/Kyle | 2017-10-13 | 2017-10-28 | 15
2.5 | Mounting Hardware Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-28 | 15
2.6 | Robotic Arm Manufacture/Assembly | Hubert/Chris/Kyle | 2017-10-13 | 2017-11-03 | 21
2.7 | Misc. Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | 18
2.8 | Design Robotic Arm Testing Rig | Rebecka | 2017-10-07 | 2017-10-14 | 7
2.9 | Manufacture Arm Testing Rig (TIG Training) | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | 18
| Milestone 3: Assembly | Mechanical Team | 2017-10-28 | 2017-12-02 | 35
3.1 | Suspension Manufacture | Mechanical Team | 2017-11-07 | 2017-11-14 | 7
3.2 | Suspension Assembly | Mechanical Team | 2017-11-14 | 2017-11-24 | 10
3.3 | Electrical Box Assembly | Riley/Kyle | 2017-10-28 | 2017-11-14 | 17
3.4 | Chassis Assembly | Derick/Rebecka/Matthew | 2017-10-28 | 2017-11-14 | 17
3.5 | Robotic Arm Off-Rover Testing | Kyle/Hubert/Chris | 2017-11-07 | 2017-12-02 | 25
3.6 | Mounting Assembly (TIG Welding) | Hubert/Chris/Other(?) | 2017-10-28 | 2017-11-19 | 22
| Milestone 4: Testing | Mechanical Team | 2017-12-02 | 2017-12-14 | 12
3.1 | LOS Driving Tests |  | 2017-12-02 | 2017-12-14 | 12
3.2 | Robotic Arm On-Rover Testing |  | 2017-12-02 | 2017-12-14 | 12
3.3 | NLOS Driving Tests |  | 2017-12-02 | 2017-12-14 | 12
3.4 | Difficult Terrain Navigation Tests |  | 2017-12-02 | 2017-12-14 | 12
3.4 | Robotic Arm Fine Manipulation Tests |  | 2017-12-02 | 2017-12-14 | 12
Formulas:
Start = [End, row above]