## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Electrical
Team Leader Name | James Talbert
Week Number | 14
Attendance Records
Number of Students Present | 50
Number of students Not Present | 10
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
We do not have an E-Box yet. We are working on the connector board for the drive system, and on refing the drive system code to allow for more robust control. We are a bit behind due to setbacks from other teams. This includes a lack of enclosures to add wiring to. We are having some trouble finding desirable connectors, due to a lack of experience with the naming conventions and such.
Task Report
Milestone/Task | Due Date | Progress | Status
Setting Up | 2017-09-06 | 100% | On Track
Assign Roles (Domain Areas) | 2017-09-20 | 100% | On Track
Get an E-Box from mechanical | 2017-09-27 | 100% | On Track
Drive System | 2017-11-12 | 100% | On Track
Do Research in needed Domains | 2017-11-12 | 100% | On Track
Power Systems | 2017-11-12 | 100% | On Track
Control Systems | 2017-11-12 | 100% | On Track
Firmware | 2017-11-12 | 100% | On Track
Circuits/CAD | 2017-11-12 | 100% | On Track
0 | 0 | 0% | On Track
Refinement | 2017-11-27 | 100% | On Track
Firmware | 2017-11-27 | 100% | On Track
Circuits | 2017-11-27 | 100% | On Track
Controls | 2017-11-27 | 100% | On Track
0 | 0 | 0% | On Track
Arm Control | 2017-12-03 | 60% | On Track
Hardware Drivers | 2017-12-03 | 100% | On Track
Firmware Drivers | 2017-12-03 | 60% | On Track
Controls | 2017-12-03 | 30% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0 | Setting Up |  |  | 2017-09-06 |  | 100%
0.1 | Assign Roles (Domain Areas) | James Talbert | 2017-09-14 | 2017-09-20 |  | 100% | bar: WEEK 4 R to WEEK 5 F
0.2 | Get an E-Box from mechanical |  | 2017-08-21 | 2017-09-27 |  | 100% | bar: WEEK 1 M to WEEK 7 F
1 | Drive System |  |  | 2017-11-12 |  | 100%
1.1 | Do Research in needed Domains | Team Members (split up) | 2017-09-27 | 2017-11-12 |  | 100% | bar: WEEK 4 R to WEEK 12 F
1.2 | Power Systems | Jake Raymer | 2017-09-27 | 2017-11-12 |  | 100% | bar: WEEK 6 M to WEEK 12 F
1.3 | Control Systems | Jefferson O'Brien | 2017-09-27 | 2017-11-12 |  | 100% | bar: WEEK 6 M to WEEK 12 F
1.4 | Firmware | Alex Vande Loo | 2017-09-27 | 2017-11-12 |  | 100% | bar: WEEK 6 M to WEEK 12 F
1.5 | Circuits/CAD | Morgan Foley | 2017-09-27 | 2017-11-12 |  | 100% | bar: WEEK 6 M to WEEK 12 F
0%
2 | Refinement |  |  | 2017-11-27 |  | 100%
2.1 | Firmware | Alex Vande Loo | 2017-11-12 | 2017-11-27 |  | 100% | bar: WEEK 13 M to WEEK 13 F
2.2 | Circuits | Morgan Foley | 2017-11-12 | 2017-11-27 |  | 100% | bar: WEEK 13 M to WEEK 13 F
| Controls | Jefferson O'Brien | 2017-11-12 | 2017-11-27 |  | 100% | bar: WEEK 13 M to WEEK 13 F
0% | bar: WEEK 13 M to WEEK 13 F
3 | Arm Control |  |  | 2017-12-03 |  | 60%
3.1 | Hardware Drivers | Morgan Foley | 2017-11-27 | 2017-12-03 |  | 100%
3.2 | Firmware Drivers | Alex Vande Loo | 2017-11-27 | 2017-12-03 |  | 60%
3.3 | Controls | Jefferson O'Brien | 2017-11-27 | 2017-12-03 |  | 30%
3.4 | Power Systems | Jake Raymer | 2017-11-27 | 2017-12-03 |  | 20%
0%
0%
0%
0%
0%
0%

## Attendance Records
NetID | First Name | Last Name | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Total
jtalbert | James | Talbert | P | P | P | P | P | P | P | P | P | P | P | P |  |  | 12
foley146 | Morgan | Foley | NP | NP | P | P | NP | NP | P | NP | P | NP | P | P |  |  | 6
jmobrien | Jefferson | O'Brien | P | P | P | P | P | P | P | P | P | P | P | P |  |  | 12
jmraymer | Jacob | Raymer | P | P | P | P | P | NP | P | P | P | NP | P | P |  |  | 10
aavande | Alexander | Vande Loo | NP | P | P | P | NP | P | P | P | P | P | P | P |  |  | 10
0
0
0
Key: | P | Present
| NP | Not Present

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track