## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Science Team
Team Leader Name | Ryan Byrnes
Week Number | 9
Attendance Records
Number of Students Present | 5
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
This week, we ordered a thermal camera, heating pad, diffraction grating, temperature sensor, humidity sensor, and printed the tube lining. We verified that the tube lining is effective. We also began to develop a script that would convert thermal emission spectrums to emissivity graphs for our spectrometer. Once we receive the parts, we will configure the spectrometer and design housing for it quickly.
Task Report
Milestone/Task | Due Date | Progress | Status
contact soil fertility lab | 2017-09-16 | 100% | On Track
Investigate locations for soil testing | 2017-09-16 | 100% | On Track
obtain force meter | 2017-09-16 | 100% | On Track
perform soil punch testing | 2017-09-16 | 100% | On Track
request sample soil from Utah | 2017-09-16 | 100% | On Track
decide on core retention device | 2017-09-20 | 100% | On Track
decide on soil tests | 2017-09-20 | 100% | On Track
decide on what type of actuator to use | 2017-09-20 | 100% | On Track
complete CAD model | 2017-09-30 | 100% | On Track
receive Utah soil | 2017-09-30 | 100% | On Track
complete CAD for spectrometer, arm attachment, tube lining, and tube cap | 2017-10-07 | 100% | On Track
complete bill of parts for full system | 2017-10-07 | 100% | On Track
schedule informal design review with matt nelson | 2017-10-13 | 100% | On Track
order parts | 2017-10-13 | 100% | On Track
configure thermal camera and grating, design housing | 2017-11-01 | 50% | On Track
test sensors | 2017-11-01 | 50% | On Track
find matlab graph script | 2017-10-14 | 100% | On Track
receive parts | 2017-10-30 | 0% | On Track
print tube caps | 2017-10-20 | 100% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE (Official Milestones NA until September 23th) | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1 - Research |  |  |  | business days | 100% | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15
1.1 | Investigate different soil gathering methods | all | 2017-09-04 | 2017-09-15 | 10 | 100%: 100%; WEEK 3 M 4: X; WEEK 3 T 5: X; WEEK 3 W 6: X; WEEK 3 R 7: X; WEEK 3 F 8: X; WEEK 4 M 11: x; WEEK 4 T 12: x; WEEK 4 W 13: x; WEEK 4 R 14: x; WEEK 4 F 15: x
1.2 | Investigate different soil analysis tests | all | 2017-09-04 | 2017-09-15 | 10 | 100%: 100%; WEEK 3 M 4: x; WEEK 3 T 5: x; WEEK 3 W 6: x; WEEK 3 R 7: x; WEEK 3 F 8: x; WEEK 4 M 11: x; WEEK 4 T 12: x; WEEK 4 W 13: x; WEEK 4 R 14: x; WEEK 4 F 15: x
1.3 | Tabulate all competition requirements into Pugh Matrix | all | 2017-09-06 | 2017-09-11 | 4 | 100%: 100%; WEEK 3 W 6: x; WEEK 3 R 7: x; WEEK 3 F 8: x; WEEK 4 M 11: x
1.4 | Agree on on-board tests | all | 2017-09-20 | 2017-09-20 | 1 | 100%: 100%; WEEK 5 W 20: x
1.5 | Agree on mechanical design | all | 2017-09-20 | 2017-09-20 | 1 | 100%: 100%; WEEK 5 W 20: x
1.6 | Obtain soil from Utah | John | 2017-09-20 | 2017-09-26 | 5 | 100%: 100%; WEEK 5 W 20: x; WEEK 5 R 21: x; WEEK 5 F 22: x; WEEK 6 M 25: x; WEEK 6 T 26: x
2 | Milestone 2 - Design | Milestone 1 - complete design
2.1 | complete CAD of collection subsystem | Brad, Ryan, Nick | 2017-09-13 | 2017-09-25 | 9 | 100%: 100%; WEEK 4 W 13: x; WEEK 4 R 14: x; WEEK 4 F 15: x; WEEK 5 M 18: x; WEEK 5 T 19: x; WEEK 5 W 20: x; WEEK 5 R 21: x; WEEK 5 F 22: x; WEEK 6 M 25: x
2.2 | parts list | Brad, Ryan | 2017-09-20 | 2017-09-22 | 3 | 100%: 100%; WEEK 5 W 20: x; WEEK 5 R 21: x; WEEK 5 F 22: x
2.3 | order sensors, rods, motor | Ryan | 2017-09-18 | 2017-09-27 | 6 | 100%: 100%; WEEK 5 M 18: x; WEEK 5 T 19: x; WEEK 5 W 20: x; WEEK 5 R 21: x; WEEK 5 F 22: x; WEEK 6 M 25: x
2.4 | 3D print as needed | Brad, Ryan, Nick | 2017-09-28 | 2017-10-06 | 7 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x; WEEK 7 M 2: x; WEEK 7 T 3: x; WEEK 7 W 4: x; WEEK 7 R 5: x; WEEK 7 F 6: x
2.5 | order spectroscope | Brad, Ryan | 2017-09-22 | 2017-09-26 | 3 | 100%: 100%; WEEK 5 F 22: x; WEEK 6 M 25: x; WEEK 6 T 26: x
2.6 | complete CAD of attachment subsystem | Brad, Ryan | 2017-09-25 | 2017-09-27 | 2 | 100%: 100%; WEEK 6 M 25: x; WEEK 6 T 26: x
2.6.1 | parts list | Brad, Ryan | 2017-09-28 | 2017-09-30 | 2 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x
2.6.2 | order parts | Brad, Ryan | 2017-09-28 | 2017-09-30 | 2 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x
2.7 | complete CAD of spectroscope subsystem | Nick, Eddie, Alex | 9/28/207 | 2017-09-30 | 2 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x
2.7.1 | parts list | Nick, Eddie, Alex | 2017-09-28 | 2017-09-30 | 2 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x
2.7.2 | order parts | Nick, Eddie, Alex | 2017-09-21 | 2017-09-30 | 2 | 100%: 100%; WEEK 6 R 28: x; WEEK 6 F 29: x
3 | Milestone 3 - Testing | Milestone 2 - all parts confirmed functional
3.1 | receive spectroscope | Ryan | 2017-09-26 | 2017-09-26 | 1 | 100%: 100%; WEEK 6 T 26: x
3.1.1 | test infrared concept, find back up test | Eddie, Nick, Alex | 2017-09-30 | 2017-09-30 | 1 | 100%: 100%; WEEK 6 F 29: x
3.1.2 | compile emission spectrum library/description for different soil types | Eddie, Nick, Alex | 2017-10-01 | 2017-10-30 | 25 | 100%: 50%; WEEK 6 F 29: x; WEEK 7 M 2: x; WEEK 7 T 3: x; WEEK 7 W 4: x; WEEK 7 R 5: x; WEEK 7 F 6: x; WEEK 8 M 9: x; WEEK 8 T 10: x; WEEK 8 W 11: x; WEEK 8 R 12: x; WEEK 8 F 13: x; WEEK 9 M 16: x; WEEK 9 T 17: x; WEEK 9 W 18: x; WEEK 9 R 19: x; WEEK 9 F 20: x; WEEK 10 M 23: x; WEEK 10 T 24: x; WEEK 10 W 25: x; WEEK 10 R 26: x; WEEK 10 F 27: x; WEEK 11 M 28: x; WEEK 11 T 29: x; WEEK 11 W 30: x
3.1.3 | multiple trials | Eddie, Nick, Alex | 2017-10-01 | 2017-10-30 | 25 | bar: 100%; WEEK 6 F 29 to WEEK 11 W 30
3.2 | receive motor | Ryan | 2017-10-20 | 2017-10-21 | 1 | bar: 100%; WEEK 9 F 20
3.2.1 | punch test for motor | James + volunteer | 2017-10-20 | 2017-10-21 | 1 | bar: 100%; WEEK 9 F 20
3.3 | receive temp and moisture sensor | James + volunteer | 2017-10-20 | 2017-10-21 | 1 | bar: 100%; WEEK 9 F 20
3.3.2 | test and calibrate | James + volunteer | 2017-10-20 | 2017-10-21 | 1 | bar: 100%; WEEK 9 F 20
3.4 | assemble and test spectroscope system | all | 2017-10-20 | 2017-10-21 | 1 | bar: 100%; WEEK 9 F 20
4 | Milestone 4 - Assembly | Milestone 3 - fully assembled and functional (spring)
4.1 | assemble collection system, spectroscope system, arm attachment | all | 2017-10-20 | 2017-11-30 | 9 | bar: 100%; WEEK 9 F 20 to WEEK 11 W 30
4.2 | integrate with arm | all | 2017-10-30 | 2017-11-30 | 1 | bar: 100%; WEEK 11 W 30
4.2.1 | electronics, wiring, coding | James + volunteer | 2017-10-30 | 2017-11-05 | 5 | bar: 100%; WEEK 11 W 30 to WEEK 12 T 5
4.3 | plan for base station procedures in Spring | all | 2017-12-01 | 2017-12-01 | 1 | bar: 100%; WEEK 13 F 15

## Attendance Records
NetID | First Name | Last Name | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Total
| Ryan | Byrnes | p | p | p | p | p | p | p | [7 empty] | 7
| Eddie | Ting | np | p | p | p | p | p | p | [7 empty] | 0
| John | Mills | p | p | p | p | np | p | p | [7 empty] | 0
| Nick | Kilzer | p | p | p | p | p | p | p | [7 empty] | 0
| Brad | Fair | p | p | p | p | p | p | p | [7 empty] | 0
| Alex | Schell | p | p | p | np | dropped team | [9 empty] | 0
0
0
Key: | Eddie John: P; Ting Mills: Present
| NP | Not Present

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track