## Gantt Chart Task List
MAVRIC
[5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Mechancial Team
M1 | Milestone 1: Design |  | 2017-08-21 | 2017-10-17 | bar: WEEK 4 M to WEEK 9 T
1.1 | Chassis CAD | Derick | 2017-09-05 | 2017-10-07 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.1.1 | Mounting Points | Rebecka/Matthew | 2017-09-05 | 2017-10-07 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.2 | Suspension CAD | Kai Davis/Jefferson O'Brien | 2017-09-05 | 2017-10-17 | bar: WEEK 4 M to WEEK 9 T; WEEK 11 M to WEEK 11 T
1.3 | Electrical Box CAD | Riley | 2017-09-12 | 2017-10-07 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4 | Robotics Arm CAD | Kyle | 2017-09-12 | 2017-10-07 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4.1 | Base Rotation | Hubert/Chris | 2017-09-19 | 2017-10-07 | bar: WEEK 5 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4.2 | Potentiometer Mount | Rebecka/Matthew | 2017-09-30 | 2017-10-07 | bar: WEEK 7 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4.3 | End Effector / Science Atttachment |  | 2017-10-03 | 2017-10-07 | bar: WEEK 7 T to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.5 | Parts List and Budget | Kyle | 2017-10-07 | 2017-10-10 | bar: WEEK 11 M to WEEK 11 T
1.6 | Integrated Assembly | Kyle | 2017-10-07 | 2017-10-10 | bar: WEEK 11 M to WEEK 11 T
M2 | Milestone 2: Manufacturing |  | 2017-10-03 | 2017-11-07 | bar: WEEK 7 T to WEEK 12 T
2.1 | Chassis Manufacturing | Quality Manufacturing | 2017-09-25 | 2017-10-17 | bar: WEEK 6 T to WEEK 9 T; WEEK 11 M to WEEK 11 T
2.1.1 | Quality Manufacturing Sponsorship | Gage/Derick | 2017-09-25 | 2017-09-25 | bar: WEEK 6 T; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.2 | Suspension Test Manufacture/Assembly | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-11-03 | bar: WEEK 8 R to WEEK 8 F; WEEK 9 T to WEEK 11 F
2.2.1 | Order/Test One Shock | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-10-31 | bar: WEEK 8 R to WEEK 8 F; WEEK 9 T to WEEK 11 T
2.2.2 | Waterjet/Manfacture Components | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-10-31 | bar: WEEK 8 R to WEEK 8 F; WEEK 9 T to WEEK 11 T
2.2.3 | Assemble and Test Suspension | Kai Davis/Jefferson O'Brien | 2017-10-17 | 2017-11-03 | bar: WEEK 8 R to WEEK 8 F; WEEK 9 T to WEEK 11 T
2.3 | Electrical Box Wooden Testbed | Riley/Kyle | 2017-10-03 | 2017-10-10 | bar: WEEK 7 T to WEEK 11 F
2.4 | Electrical Box Manufacture | Riley/Kyle | 2017-10-13 | 2017-10-28 | bar: WEEK 8 R to WEEK 11 T
2.5 | Mounting Hardware Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-28 | bar: WEEK 8 R to WEEK 11 T
2.6 | Robotic Arm Manufacture/Assembly | Hubert/Chris/Kyle | 2017-10-13 | 2017-11-03 | bar: WEEK 8 R to WEEK 11 F
2.7 | Misc. Manufacture | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | bar: WEEK 8 R to WEEK 11 T
2.8 | Design Robotic Arm Testing Rig | Rebecka | 2017-10-07 | 2017-10-14 | bar: WEEK 11 M to WEEK 11 T
2.9 | Manufacture Arm Testing Rig (TIG Training) | Rebecka/Matthew | 2017-10-13 | 2017-10-31 | bar: WEEK 8 R to WEEK 11 T
M3 | Milestone 3: Assembly |  | 2017-10-28 | 2017-12-02 | bar: WEEK 11 M to WEEK 14 F
3.1 | Suspension Manufacture | Mechanical Team | 2017-11-07 | 2017-11-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 12 T to WEEK 13 T
3.2 | Suspension Assembly | Mechanical Team | 2017-11-14 | 2017-11-24 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 13 T to WEEK 14 M
3.3 | Electrical Box Assembly | Riley/Kyle | 2017-10-28 | 2017-11-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 10 F to WEEK 13 T
3.4 | Chassis Assembly | Derick/Rebecka/Matthew | 2017-10-28 | 2017-11-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 10 F to WEEK 13 T
3.5 | Robotic Arm Off-Rover Testing | Kyle/Hubert/Chris | 2017-11-07 | 2017-12-02 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 12 T to WEEK 14 F
3.6 | Mounting Assembly (TIG Welding) | Hubert/Chris/Other(?) | 2017-10-28 | 2017-11-19 | bar: WEEK 8 R to WEEK 8 F; WEEK 10 F to WEEK 13 R
M4 | Milestone 4: Testing |  | 2017-12-02 | 2017-12-14 | bar: WEEK 14 F to WEEK 15 F
4.1 | LOS Driving Tests |  | 2017-12-02 | 2017-12-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 14 F to WEEK 15 F
4.2 | Robotic Arm On-Rover Testing |  | 2017-12-02 | 2017-12-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 14 F to WEEK 15 F
4.3 | NLOS Driving Tests |  | 2017-12-02 | 2017-12-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 14 F to WEEK 15 F
4.4 | Difficult Terrain Navigation Tests |  | 2017-12-02 | 2017-12-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 14 F to WEEK 15 F
4.5 | Robotic Arm Fine Manipulation Tests |  | 2017-12-02 | 2017-12-14 | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T; WEEK 14 F to WEEK 15 F
Science Team
1 | Milestone 1: Research |  |  | 2017-09-29 | bar: WEEK 4 M to WEEK 6 F
1.1 | Investigate different soil gathering methods |  | 2017-09-04 | 2017-09-15 | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.2 | Investigate different soil analysis tests |  | 2017-09-04 | 2017-09-15 | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.3 | Tabulate all competition requirements into Pugh Matrix |  | 2017-09-06 | 2017-09-11 | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4 | Agree on on-board tests |  |  | 2017-09-20 | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.5 | Agree on mechanical design |  |  | 2017-09-20 | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.6 | Obtain soil from Utah |  | 2017-09-20 | 2017-09-26 | bar: WEEK 5 M to WEEK 6 T; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2 | Milestone 2: Design |  |  | 2017-10-14 | bar: WEEK 4 M to WEEK 8 F
2.1 | Complete CAD of collection subsystem |  | 2017-09-13 | 2017-09-25 | bar: WEEK 4 W to WEEK 6 M; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.2 | Parts list |  | 2017-09-20 | 2017-09-22 | bar: WEEK 4 F to WEEK 5 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.3 | Order sensors, rods, motor |  | 2017-09-18 | 2017-09-27 | bar: WEEK 5 M to WEEK 6 T; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.4 | 3D print as needed |  |  | 2017-10-06 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.5 | Order spectroscope |  | 2017-09-22 | 2017-09-26 | bar: WEEK 5 M to WEEK 6 T; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.6 | Complete CAD of attachment subsystem |  | 2017-09-25 | 2017-09-27 | bar: WEEK 5 M to WEEK 6 W; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.6.1 | Parts list |  |  | 2017-09-27 | bar: WEEK 4 M to WEEK 6 W; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.6.2 | Order parts |  |  | 2017-09-27 | bar: WEEK 4 M to WEEK 6 W; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.7 | Complete CAD of spectroscope subsystem |  |  | 2017-09-29 | bar: WEEK 4 M to WEEK 6 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.7.1 | Parts list |  |  | 2017-09-29 | bar: WEEK 4 M to WEEK 6 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.7.2 | oOder parts |  |  | 2017-09-29 | bar: WEEK 4 M to WEEK 6 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3 | Milestone 3: Testing |  |  | 2017-11-07 | bar: WEEK 4 M to WEEK 12 F
3.1 | Receive spectroscope |  |  | 2017-09-26 | bar: WEEK 4 M to WEEK 6 W; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.1.1 | Find out how much dilution is needed | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.1.2 | Compile emission spectrum library/description for different soil types | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.1.3 | Multiple trials | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.2 | Receive motor | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.2.1 | Punch test for motor | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.3 | Receive temp and moisture sensor | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.3.1 | Test and calibrate | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.4 | Assemble and test spectroscope system | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
Strategy Team
1 | Milestone 1: Technical Advising |  |  | 2017-12-01
1.1 | Advise E-Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
1.2 | Advise Science Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
1.3 | Advise Mechanical Team | Gabe / Isaiah | 2017-09-12 | 2017-12-01
2 | Milestone 2: Rover Simulator |  |  | 2017-11-18 | bar: WEEK 4 M to WEEK 13 F
2.1 | Basic Controls | Isaiah | 2017-09-12 | 2017-10-06 | bar: WEEK 4 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.2 | Camera feedback | Isaiah | 2017-09-12 | 2017-10-14 | bar: WEEK 4 M to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.3 | Rover Rigging | Isaiah | 2017-09-12 | 2017-10-28 | bar: WEEK 4 M to WEEK 11 T
2.4 | Game elements | Isaiah | 2017-09-12 | 2017-11-18 | bar: WEEK 4 M to WEEK 13 F
3 | Milestone 3: Mavric Cockpit |  |  | 2017-10-28 | bar: WEEK 4 M to WEEK 10 F
3.1 | Decide on Cockpit Style | Isaiah | 2017-09-12 | 2017-10-14 | bar: WEEK 4 M to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.2 | Build Control system / Hardware | Gabe | 2017-09-12 | 2017-10-28 | bar: WEEK 4 M to WEEK 11 T
Electrical Team
1 | Milestone 1: Drive system |  |  | 2017-11-12 | bar: WEEK 4 M to WEEK 12 F
1.1 | Do reasearch | Split among team | 2017-09-14 | 2017-09-27 | bar: WEEK 4 W to WEEK 6 W; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.2 | Power systems | Jake Raymer | 2017-09-21 | 2017-10-04 | bar: WEEK 5 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.3 | Control systems | Jefferson O'Brien | 2107-09-21 | 2017-10-04 | bar: WEEK 5 M to WEEK 7 F; WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.4 | Firmware | Alex Vande Loo | 2017-09-21 | 2017-10-11 | bar: WEEK 5 M to WEEK 8 F; WEEK 11 M to WEEK 11 T
1.5 | Circuits CAD | Morgan Foley | 2017-09-21 | 2017-10-11 | bar: WEEK 5 M to WEEK 8 F; WEEK 11 M to WEEK 11 T
2 | Milestone 2: Refinement |  |  | 2017-11-27
2.1 | Firmware | Alex Vande Loo | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.2 | Circuits | Morgan Foley | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
2.3 | Controls | Jefferson O'Brien | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3 | Milestone 3: Drive system |  |  | 2017-12-03
3.1 | Hardware Drivers | Morgan Foley | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.2 | Firmware Drivers | Alex Vande Loo | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.3 | Controls | Jefferson O'Brien | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T
3.4 | Power systems | Jake Raymer | bar: WEEK 8 R to WEEK 8 F; WEEK 11 M to WEEK 11 T